## AAOS VAPT Work Plan
Work Package ID | Task ID | Task Name | Description | Depends On | Start Date | End Date | Status | Deliverables
WP1 | WP1.1 | Setup AAOS Emulator | Configure AAOS virtual device using Android Studio | – | 01-Jun-2025 | 03-Jun-2025 | Not Started | Emulator screenshot, device config
WP1 | WP1.2 | Toolchain Setup | Install ADB, Frida, MobSF, mitmproxy | – | 01-Jun-2025 | 04-Jun-2025 | Not Started | Tools installed and verified
WP2 | WP2.1 | AAOS Architecture Mapping | Diagram AAOS components, services, HAL layers | WP1.1 | 05-Jun-2025 | 08-Jun-2025 | Not Started | AAOS architecture diagram
WP2 | WP2.2 | Attack Surface Identification | Identify exposed APIs, wireless interfaces | WP2.1 | 08-Jun-2025 | 10-Jun-2025 | Not Started | Attack surface map, threat model
WP3 | WP3.1 | APK Extraction | Extract system APKs from AAOS using ADB | WP1.1 | 09-Jun-2025 | 10-Jun-2025 | Not Started | List of APKs, extraction logs
WP3 | WP3.2 | Static Analysis | Run MobSF, JADX, APKTool for APK review | WP3.1, WP1.2 | 10-Jun-2025 | 13-Jun-2025 | Not Started | Static analysis report, MobSF scan
WP4 | WP4.1 | Runtime Behavior Monitoring | Use ADB logcat and Frida to inspect app behavior | WP3.2 | 14-Jun-2025 | 16-Jun-2025 | Not Started | Hook results, logcat analysis
WP5 | WP5.1 | Network Interception Setup | Setup mitmproxy between phone and AAOS emulator | WP1.2 | 14-Jun-2025 | 15-Jun-2025 | Not Started | mitmproxy capture files
WP5 | WP5.2 | Wireless Attack Simulation | Test Bluetooth/Wi-Fi interfaces, intent sniffing | WP2.2 | 16-Jun-2025 | 18-Jun-2025 | Not Started | Wireless testing logs, intent hijack PoC
WP6 | WP6.1 | Reporting & Documentation | Compile results, findings, mitigations | WP3.2, WP4.1, WP5.2 | 19-Jun-2025 | 22-Jun-2025 | Not Started | Final report, screenshots, vulnerability list